## Defect Details
Defect ID | Module Name | Defect Description | Defect Severity | Defect Priority | Defect Type | Defect Raised On | Status | Tester Comment | Developer Comment | Assign To
Defect_FT_001 | Tickets | ADMIN Login --> New Ticket --> Please fix localization in file type validation in Supporting Documents. | Low | P3 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_002 | Tickets | ADMIN Login -->New Ticket --> Supporting Documents --> User able to upload more than 3 documents although a/c validation maximum 3 documents can be uploaded. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_003 | Tickets | ADMIN Login --> Ticket Details -->Take Action --> ‘REJECT’ button is not clearly visible. | Medium | P2 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_004 | Tickets | ADMIN Login --> Inbox --> Appling ‘Ticket Type’ filter as Battery shows all tickets having battery as ticket type but if we add another ticket type it shows ‘No Records Found’. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_005 | Tickets | Login- CSR User --> Inbox --> Appling ‘Health Care Centre’ filter as Aidbhavi shows all tickets of that subcentre but if we add another health care centre, it shows ‘No Records Found’. | High | P1 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_006 | Tickets | Generic Issue --> Label has ‘Center’ and dropdown values have ‘Centre’. Please correct the spelling and use a common term everywhere. | Low | P3 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_007 | Tickets | CSR User --> Ticket Summary Page --> Documents uploaded while creating a ticket is not visible in ticket summary. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_008 | Tickets | Generic Issue --> Reject Ticket Popup --> Please fix localization. | Low | P3 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 16/12/2024
Defect_FT_009 | Tickets | Generic Issue --> Reject Ticket Popup --> ‘Comments’ field is marked mandatory, but user is able to Reject the ticket without entering the comments. | Medium | P2 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_010 | Tickets | Generic Issue --> After doing any action on a ticket and then clicking home page and finally going to the inbox. User needs to refresh the inbox page then the updated status of the ticket appears although in the ticket summary page the status gets updated instantly. Same issue for ticket creation. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 16/12/2024
Defect_FT_011 | Tickets | Generic Issue --> Send Back button is not clearly visible | Medium | P2 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_012 | Tickets | Generic Issue --> Inbox --> ‘Assigned to Me’ and ‘Assigned to All’ filters are not working. Same number of tickets are displayed in each case | Medium | P2 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_013 | Tickets | In the Inbox page, The ticket text box and the search button should be properly aligned. | Medium | P2 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_014 | Tickets | In the new ticket creation page, the choose file control label should be placed in the central alignment. | Low | P3 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_015 | Tickets | Resolve Ticket. The validation message needs to be changed as ‘Please upload mandatory document’ instead of ‘Please enter mandatory fields’. | Medium | P2 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 16/12/2024
Defect_FT_016 | Tickets | Getting validation message even after user uploaded a valid word document. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 16/12/2024
Defect_FT_017 | Tickets | Please fix the localization in the ‘View Profile’ label. | Medium | P2 | UI | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_018 | Tickets | Side Menu: Search functionality is not working properly in S8+ mobile response. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 16/12/2024
Defect_FT_019 | Tickets | Mobile responsive: Geeting error page on clicking inbox link. (User: SHIVANICMO (Complainant), Env: 'Samsung Galaxy S8+' device). | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024
Defect_FT_020 | Tickets | I-Pad mini responsive issue. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 26/12/2024
Defect_FT_021 | Tickets | iPhone SE à Mobile Responsive Issue. | High | P1 | Functional | 2024-12-12 | Closed | Refer Screenshots in the word doc sent on 12/12/2024. Retest failed on 26/12/2024
Defect_FT_022 | Tickets | Generic Issue --> When search filters like ticket types or Health Care Center are applied --> The ticket count in the status filter doesn’t match the count at the bottom of the page. | High | P1 | Functional | 2024-12-16 | Closed | Refer Screenshots in the word doc sent on 16/12/2024.
Defect_FT_023 | Tickets | Reject Ticket Popup --> Validation message shows ‘Comments are mandatory’ but Reject reasons are also mandatory. Please correct the validation message sequence. | Medium | P1 | Functional | 2024-12-16 | Closed | Refer Screenshots in the word doc sent on 16/12/2024.
Defect_FT_024 | Tickets | ADMIN, ASSESSOR Login --> Unable to reject a ticket | Critical | P1 | Functional | 2024-12-16 | Closed | Refer Screenshots in the word doc sent on 16/12/2024.
Defect_FT_025 | Tickets | ADMIN Login --> While creating a ticket if the user enters long comment, then in the ticket summary the details don’t appear. Ticket No --> KA-RCH-001-0158 | High |  | Functional | 2024-12-19 | Closed | Refer Screenshots in the word doc sent on 19/12/2024.
Defect_FT_026 | Tickets | ADMIN Login --> If we apply any status filter, then the count on the other status filter types becomes zero. | High |  | Functional | 2024-12-19 | Closed | Refer Screenshots in the word doc sent on 19/12/2024.
Defect_FT_027 | Tickets | Generic Issue --> User unable to logout using the logout button link in the side menu | Critical |  | Functional | 2024-12-19 | Closed | Refer Screenshots in the word doc sent on 19/12/2024.
Defect_FT_028 | Tickets | Generic Issue --> ‘Assigned to Me’ and ‘Assigned to All’ filters are not working | High |  | Functional | 2024-12-19 | Closed | Refer Screenshots in the word doc sent on 20/12/2024.
Defect_FT_029 | Tickets | Generic Issue --> Inbox --> When applied ticket type filter and user moves to the next page --> Selects status filter shows no records found. User should be moved to page 1 as there are only 9 tickets. | High |  | Functional | 2024-12-20 | Closed | Refer Screenshots in the word doc sent on 19/12/2024.
Defect_FT_030 | Tickets | ADMIN Login --> Inbox Page --> Assigned to me filter is applied shows no records but in status filter ticket count is still there | Medium |  | Functional | 2024-12-20 | Closed | Refer Screenshots in the word doc sent on 20/12/2024.
Defect_FT_031 | Tickets | ADMIN Login --> Ticket count changes when we apply status filter. Refer screenshots below --> Like Pending Resolution has 14 tickets which changes to 12 when resolved filter is unchecked. | Medium |  | Functional | 2024-12-27 | Closed | Refer Screenshots in the word doc sent on 20/12/2024.